THE SPEC-DRIVEN DEVELOPMENT

FRAMEWORK

From Idea to Executable Agent Prompts

A Replicable Methodology for AI-Assisted Software Development

Developed by: Chrix @ 1322 Legacy Strategies

January 2026

# Table of Contents

# Executive Summary

This document captures a proven methodology for transforming any software idea into a fully executable build plan. The process works by front-loading all specification and documentation work before writing a single line of code, then using those specifications to generate a Product Development Roadmap (PDR) along with individual agent prompts for every task.

Core Principle Write the complete documentation first. Let the specifications drive the code, not the other way around.

The methodology produces:

- Complete technical specifications before any code is written

- A structured PRD (Product Requirements Document) derived from specifications

- Individual executable agent prompts for each development task

- A dependency graph showing parallelization opportunities

- Quality gates and acceptance criteria for every deliverable

# 1. The Framework Overview

## 1.1 The Three-Phase Approach

The Spec-Driven Development Framework consists of three distinct phases, each building on the previous:

### Phase 1: Specification Development

Before any code exists, create comprehensive documentation covering architecture, data models, security requirements, operational procedures, and engineering practices. This phase produces 50+ specification documents organized by domain.

### Phase 2: PRD Generation

Feed the specifications to Claude with a PRD prompt template. The AI synthesizes all specifications into a cohesive Product Requirements Document with sprint decomposition, functional requirements, and success criteria.

### Phase 3: Agent Prompt Generation

Generate individual build prompts for every task identified in the PRD. Each prompt contains everything an AI coding agent needs to complete the task: context, prerequisites, TDD instructions, acceptance criteria, and security checklists.

| Phase | Input | Output | Key Activities |
| --- | --- | --- | --- |
| 1. Specification | Raw idea + domain knowledge | 50+ spec documents | Architecture design, schema definition, policy creation |
| 2. PRD Generation | All spec documents | Structured PRD with sprints | Requirements synthesis, sprint planning, risk analysis |
| 3. Agent Prompts | PRD + spec references | 100+ executable prompts | Task decomposition, dependency mapping, TDD structure |

## 1.2 Why This Works

Traditional development often suffers from incomplete requirements and scope creep. By forcing comprehensive specification upfront, this methodology:

- Eliminates ambiguity before development starts

- Creates a single source of truth that all prompts reference

- Enables parallel execution by identifying task dependencies

- Ensures consistent quality through standardized prompt templates

- Reduces iteration cycles by catching design issues early

# 2. Phase 1: Specification Development

## 2.1 Documentation Structure

Organize specifications into numbered directories that cover all aspects of the system. Here is the proven structure:

| Directory | Purpose | Key Documents |
| --- | --- | --- |
| 00-overview | Project vision and scope | Executive summary, documentation index |
| 01-architecture | System design | System architecture, integration specs |
| 02-schemas | Data models | Database schemas, API contracts |
| 03-agents-tools | Agent definitions | Tool registry, recursion contracts |
| 04-[domain-specific] | Domain-specific specs | Varies by project |
| 05-policy-safety | Security and compliance | Threat model, RBAC, tenant isolation |
| 06-reliability-ops | Operations | SLOs, incident runbooks, observability |
| 07-engineering-process | Development practices | Handbook, testing strategy, CI/CD |
| adr | Decision records | Architecture Decision Records |
| runbooks | Operational procedures | Incident response procedures |

## 2.2 Essential Specification Documents

Every project should include these core specifications:

### Architecture Documents

- System Architecture: Components, data flow, integration points

- Data Model: Entity definitions, relationships, constraints

- Integration Spec: External system connections, API patterns

### Engineering Documents

- Engineering Handbook: Code standards, PR discipline, testing requirements

- Testing Strategy: Test pyramid, coverage requirements, critical paths

- CI/CD Specification: Pipeline stages, deployment gates, environments

### Security Documents

- Threat Model: Attack surfaces, mitigations, data flow analysis

- Multi-Tenant Isolation: Tenant context, query scoping, fail-closed policies

- Secrets Management: Credential handling, rotation, access patterns

### Operations Documents

- SLO/Error Budget: Reliability targets, measurement, burn rate policies

- Observability: Metrics, logging, dashboards, alerting

- Incident Runbooks: Response procedures for common scenarios

## 2.3 Writing Effective Specifications

Specifications should be:

- Concrete: Include specific values, thresholds, and examples

- Testable: Define acceptance criteria that can be verified

- Referenced: Use consistent naming so prompts can point to specific sections

- Complete: Cover happy paths, edge cases, and failure modes

Specification Quality Test If you can&#x2019;t write a test for it, the specification isn&#x2019;t specific enough. Every requirement should have measurable acceptance criteria.

# 3. Phase 2: PRD Generation

## 3.1 The PRD Prompt Template

Feed all specifications to Claude with a structured prompt that requests synthesis into a PRD. The prompt should request:

### Executive Summary

- Vision statement derived from specifications

- Core differentiators and key architecture concepts

- Platform scope and phasing

### Functional Requirements

- Requirements organized by subsystem (FR-XX numbering)

- Each requirement traceable to specification source

- Clear acceptance criteria

### Non-Functional Requirements

- Performance targets (SLOs) from reliability specs

- Security requirements from threat model

- Observability requirements from ops specs

### Sprint Decomposition

- Sprints organized by capability delivery

- Parallel agent tracks (A, B, C, D) within each sprint

- Clear dependencies and blocked work identification

- Deliverables checklist per sprint

## 3.2 Sprint Planning Principles

When decomposing work into sprints:

- Foundation First: Infrastructure, schema, CI/CD before features

- Parallel Tracks: 4 agents working simultaneously within each sprint

- No Side Effects Early: Build creation/drafting before publishing

- Safety Gates Last: Kill switches and rollout controls in final sprint

| Sprint Pattern | Focus | Typical Deliverables |
| --- | --- | --- |
| Sprint 0 | Foundation | Repo structure, database schema, CI/CD, observability |
| Sprint 1 | Core Infrastructure | Domain models, memory layer, policy engine, runner |
| Sprint 2-N | Feature Development | Business logic, agent prompts, integrations |
| Final Sprint | Gated Rollout | Testing, kill switches, canary deployment, E2E validation |

## 3.3 Agent Track Design

Each sprint should have 4 parallel agent tracks:

| Track | Typical Focus | Example Tasks |
| --- | --- | --- |
| Agent A | Core domain/models | Entity definitions, API endpoints, business logic |
| Agent B | Data layer | Schema, migrations, queries, caching |
| Agent C | Infrastructure | CI/CD, deployment, configuration, security |
| Agent D | Cross-cutting concerns | Observability, testing, documentation |

# 4. Phase 3: Agent Prompt Generation

## 4.1 The Build Prompt Template

Every task identified in the PRD becomes an executable build prompt. The prompt template ensures consistency and completeness:

### Metadata Block

Structured information for tracking and orchestration:

- Task ID: Sprint-Agent-Number format (e.g., S0-A1)

- Complexity rating: Low/Medium/High

- Estimated hours

- Dependencies and blocks

- Status tracking

### Context Section

What the task builds and why it matters:

- 2-4 sentences explaining the task purpose

- Connection to larger system architecture

- Spec references with specific section anchors

### Prerequisites

Everything needed before starting:

- Completed tasks (hard dependencies)

- Required tools and packages

- Required accounts and access

### Instructions (TDD Format)

Three-phase implementation approach:

- RED: Write failing tests first

- GREEN: Implement minimum code to pass

- REFACTOR: Clean up without changing behavior

### Acceptance Criteria

Specific, testable criteria for completion:

- Exact commands to run for verification

- Expected outputs and behaviors

- Quality gates (tests pass, lint pass, typecheck pass)

### Security Checklist

Safety verification for every task:

- No hardcoded secrets

- Tenant isolation enforced

- Audit events emitted (if side effects)

- Kill switches checked (if side effects)

## 4.2 JSON Task Block

Each prompt includes a machine-parseable JSON block for orchestration tools:

JSON Schema task_id, name, sprint, agent, status, dependencies, blocks, estimated_complexity, acceptance_criteria, spec_references, test_files, created_files

## 4.3 Context Injection Principles

Build prompts should reference specifications without duplicating content:

### Reference Patterns

- Full path references: /docs/path/to/spec.md#section

- Section anchors for large documents

- Brief descriptions of what to find

### When to Quote Directly

Only quote specifications directly for:

- Critical security constraints

- Non-negotiable invariants

- Easy-to-miss requirements

# 5. Dependency Management

## 5.1 The Dependency Graph

A critical output of the framework is the task dependency graph. This enables:

- Parallel execution identification

- Critical path analysis

- Blocked work visibility

- Sprint planning optimization

## 5.2 Dependency Types

| Type | Symbol | Description |
| --- | --- | --- |
| Sequential | ───▶ | Must complete first within same agent track |
| Cross-Agent | ═══▶ | Dependency across different agent tracks |
| Cross-Sprint | ╌╌╌▶ | Implicit dependency on previous sprint completion |

## 5.3 Critical Path Analysis

Identify the longest dependency chain to determine minimum completion time. In a well-designed PRD:

- Critical path should be ~30% of total tasks

- ~70% of tasks can run in parallel

- Cross-agent dependencies should be minimized

# 6. Implementation Checklist

## 6.1 Phase 1 Checklist: Specifications

- Create directory structure (00-overview through 09+)

- Write executive summary with vision and scope

- Define system architecture with data model

- Create all schema definitions

- Document security requirements and threat model

- Define SLOs and observability requirements

- Write engineering handbook with code standards

- Create testing strategy with coverage requirements

- Document CI/CD pipeline specification

- Write operational runbooks

- Create ADR index and initial decisions

## 6.2 Phase 2 Checklist: PRD

- Synthesize all specs into executive summary

- Extract functional requirements with FR-XX numbering

- Define non-functional requirements with specific targets

- Decompose into sprints (typically 5-6 sprints)

- Assign 4 agent tracks per sprint

- Identify 5 tasks per agent per sprint

- Map dependencies between tasks

- Define success criteria and risks

## 6.3 Phase 3 Checklist: Agent Prompts

- Create prompt template with all sections

- Generate prompts for every task (100+ total)

- Include TDD instructions in every prompt

- Add JSON task blocks for orchestration

- Create dependency graph visualization

- Write context injection guide

- Validate all spec references are valid

# 7. Applying the Framework to New Ideas

## 7.1 Starting from Scratch

When you have a new idea, follow this sequence:

- Brain Dump: Write everything you know about the idea

- Domain Analysis: Identify the key domains and subsystems

- Create Directory Structure: Set up the documentation hierarchy

- Write Core Specs First: Architecture, data model, security

- Fill in Domain Specs: Features, integrations, operations

- Generate PRD: Feed specs to Claude with PRD prompt

- Generate Agent Prompts: Create individual task prompts

- Build Dependency Graph: Visualize task relationships

- Begin Execution: Start with Sprint 0, Agent A, Task 1

## 7.2 Specification Prompt Templates

Use these prompts to generate initial specifications from your idea description:

### Architecture Spec Prompt

Template Given this idea: [IDEA], create a system architecture document covering: 1) System components, 2) Data flow, 3) Integration points, 4) Technology stack, 5) Data model with entities and relationships

### Security Spec Prompt

Template Given this architecture: [ARCH], create a security specification covering: 1) Threat model, 2) Authentication/authorization, 3) Data protection, 4) Tenant isolation (if multi-tenant), 5) Audit requirements

### PRD Generation Prompt

Template Given these specifications: [ALL SPECS], create a PRD with: 1) Executive summary, 2) Functional requirements (FR-XX), 3) Non-functional requirements, 4) Sprint decomposition with 4 parallel agent tracks, 5) Success criteria, 6) Risks and mitigations

## 7.3 Quality Validation

Before executing, validate:

- Every functional requirement traces to a specification

- Every task has clear acceptance criteria

- All dependencies are mapped

- Security checklist applies to all side-effect tasks

- Critical path is identified

# 8. Key Principles

## 8.1 Non-Negotiable Rules

These rules apply to every project using this framework:

- Never implement without tests first (TDD)

- Never skip acceptance criteria verification

- Always emit audit events for side effects

- Always check kill switches before side effects

- Always include tenant context in multi-tenant systems

- Never store secrets in code or database

- Small batches: PRs should be reviewable in 10-20 minutes

## 8.2 The Reference Principle

Build prompts reference specifications; they don&#x2019;t duplicate them. This ensures:

- Single source of truth (specs can update without updating prompts)

- Prompts stay focused on &#x201C;how to build&#x201D;

- Consistency across all tasks

## 8.3 The Parallelization Principle

Design sprints for maximum parallel execution. Four agents should be able to work simultaneously with minimal blocking.

## 8.4 The Incremental Value Principle

Each sprint should deliver working, testable functionality. Never batch all testing or integration to the end.

# Conclusion

The Spec-Driven Development Framework transforms the chaotic process of software development into a systematic, repeatable methodology. By investing heavily in upfront specification, you create a foundation that enables:

- Clear requirements that eliminate ambiguity

- Executable prompts that any AI agent can follow

- Parallel development that maximizes team velocity

- Consistent quality through standardized templates

- Predictable delivery through dependency management

The methodology has been proven on complex, multi-sprint projects and scales from simple applications to enterprise systems. The key is discipline: complete the specifications before generating the PRD, and complete the PRD before generating agent prompts.

Remember The specifications are the product. The code is just their implementation.

---

Document generated from the RTV Social Automation project methodology